ohbobi

Diet Planner CLI — Product Backlog & Sprint Schedule

Computer Science Course Project  |  Sprint-Ready Scrum Artefact  |  April 2026

# 1. Product Vision & Scope

ohbobi is a secure, ergonomic command-line diet planner written in C23. It follows the Unix philosophy of doing one thing well and integrates naturally alongside tools like git, dotnet, and cargo. All data is stored in a single structured binary file; no external database is required.

Target audience: computer science students and professionals who prefer keyboard-driven tools and want nutrition planning integrated into their terminal workflow.

## 1.1 Command Surface

| Command | Flag(s) | Description |
| --- | --- | --- |
| ohbobi nmp | (none) | Create meal plan for tomorrow (interactive) |
| ohbobi nmp | <date> | Create meal plan for a specific date |
| ohbobi nmp | -w | Create a full 7-day weekly plan from today |
| ohbobi smp | (none) | Open the interactive grid viewer |
| ohbobi --help |  | Print usage information |

# 2. Definition of Done (DoD)

A story is DONE when all of the following are true:

- Code compiles with gcc -std=c23 -Wall -Wextra -Wformat-security -Wshadow with zero warnings

- All acceptance criteria in the story are verifiably met

- Unit tests covering the changed code exist and pass under make test

- No calls to gets(), sprintf(), system(), or popen() anywhere in the changed files

- Code reviewed by at least one other team member

- Relevant section of README.md updated

# 3. Epics

| Epic ID | Title | Primary Module | Sprint(s) |
| --- | --- | --- | --- |
| EP-01 | CLI Entry Point & App Bootstrap | main.c / args.c | 1 |
| EP-02 | Data Storage (Binary File Layer) | storage.c | 1–2 |
| EP-03 | New Meal Plan (ohbobi nmp) | nmp.c / date.c | 2–3 |
| EP-04 | Show Meal Plan Grid (ohbobi smp) | smp.c / grid.c | 3–4 |
| EP-05 | Security & Input Hardening | All modules | 2, 5 |
| EP-06 | Build, Test & Documentation | Makefile / tests/ | 1, 3, 5 |

# 4. User Story Backlog

Each story follows the format: "As a user, I want to… so that…". Story points use modified Fibonacci (1, 2, 3, 5, 8, 13).

## EP-01 — CLI Entry Point & App Bootstrap

Establish the ohbobi binary, argument parser, and top-level command dispatch.

| US-01 | Install ohbobi as a system command | Priority: High | Points: 3 | Sprint: 1 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Binary is placed in /usr/local/bin or equivalent - Running ohbobi --help prints usage - Running ohbobi with no args shows a friendly error

| US-02 | Argument parsing & command dispatch | Priority: High | Points: 5 | Sprint: 1 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - ohbobi nmp dispatches to New Meal Plan module - ohbobi smp dispatches to Show Meal Plan module - Unknown commands print usage and exit with code 1 - Flags (-w) are forwarded correctly to sub-commands

| US-03 | Input sanitisation layer | Priority: Critical | Points: 5 | Sprint: 1 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - All user inputs are validated against an allowlist - Shell metacharacters are rejected before any processing - Inputs exceeding max length are rejected with a clear message - No system() or popen() calls are ever made with user data

## EP-02 — Data Storage (Binary File Layer)

Design and implement the flat-file persistence layer using a structured binary format suitable for C.

| US-04 | Define binary file format and header | Priority: Critical | Points: 5 | Sprint: 1 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - File starts with magic bytes and version field - Header stores record count and schema version - Format is documented in a SPEC.md companion file

| US-05 | CRUD operations for meal plan records | Priority: High | Points: 8 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Create: appends a new day record to the file - Read: reads a record by date key in O(n) - Update: overwrites an existing record in-place - Delete: marks record as deleted (soft delete)

| US-06 | File integrity and atomic writes | Priority: High | Points: 5 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Writes use a temp file + rename pattern (atomic) - CRC32 checksum is validated on every open - Corrupt file produces a clear error and recovery prompt

## EP-03 — New Meal Plan (ohbobi nmp)

Interactive terminal flow for creating and editing daily or weekly meal plans.

| US-07 | Single-day plan creation — default tomorrow | Priority: High | Points: 5 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Running ohbobi nmp defaults date to tomorrow - Date is printed clearly before input begins - User enters up to 3 meals per day - Each meal accepts up to 8 ingredients

| US-08 | Custom date input with multi-format support | Priority: High | Points: 5 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Prompts user for date when no default applies - Accepts: YYYY-MM-DD, DD/MM/YYYY, DD Mon YYYY, "next Monday", "tomorrow", ISO 8601 - Invalid date shows a specific error and re-prompts - All parsing done in C without exec of date(1)

| US-09 | Weekly plan mode (-w flag) | Priority: High | Points: 8 | Sprint: 3 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - ohbobi nmp -w starts a 7-day plan from today - User iterates through each day in sequence - Progress indicator shows current day (e.g. Day 3/7) - Partially completed week plan is saved on CTRL+C

| US-10 | Conflict detection and overwrite prompt | Priority: High | Points: 5 | Sprint: 3 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Before writing, existing plans for the target date are checked - Existing plan is rendered in the terminal before the prompt - User chooses: (o)verwrite, (k)eep, (s)kip for each conflict - Decision is applied per-day; other days are unaffected

| US-11 | Meal input UX — inline editor | Priority: Medium | Points: 8 | Sprint: 3 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Arrow-key navigation between meals and ingredients - Tab advances to next field; Shift+Tab goes back - CTRL+D finishes the current day plan - Input fields have a visible max-char indicator

## EP-04 — Show Meal Plan Grid (ohbobi smp)

Responsive terminal grid viewer with daily, weekly, and monthly views.

| US-12 | Responsive grid renderer (daily view) | Priority: High | Points: 8 | Sprint: 3 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Detects terminal width via ioctl(TIOCGWINSZ) - Single column full-day view at <80 cols - Grid adapts cell width proportionally up to 220 cols - Meals and ingredients truncate with … if too wide

| US-13 | Weekly grid view | Priority: High | Points: 8 | Sprint: 4 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - 7 columns, one per day, current day highlighted - Each cell shows 3 meals with up to 5 ingredients each - Cells scroll vertically if content overflows - Column widths are equal and fill terminal width

| US-14 | Monthly grid view | Priority: Medium | Points: 8 | Sprint: 4 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Calendar-style 7-column month grid - Days with meal plans show a brief preview line - Empty days are visually distinct - Month name and year shown in header

| US-15 | Keyboard navigation (vim-style) | Priority: High | Points: 5 | Sprint: 4 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - i toggles interval: daily → weekly → monthly → daily - n advances to next week/month - N (Shift+n) goes to previous week/month - q or ESC exits the viewer - Arrow keys or hjkl move focus between cells in weekly view

| US-16 | ANSI color theme and borders | Priority: Medium | Points: 5 | Sprint: 4 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Unicode box-drawing characters for grid borders - Current day cell highlighted with a distinct color - Graceful fallback to ASCII borders when TERM is dumb - App respects NO_COLOR env variable

## EP-05 — Security & Input Hardening

Ensure no user input can lead to command injection, buffer overflows, or path traversal.

| US-17 | Bounded string input everywhere | Priority: Critical | Points: 5 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - All fgets / read calls specify a hard buffer limit - No sprintf — only snprintf with explicit sizes - Ingredient names capped at 64 chars; meal names at 128 chars - All truncations logged with a warning

| US-18 | Path traversal prevention for data file | Priority: Critical | Points: 3 | Sprint: 2 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Data file path is set at compile time or via XDG_DATA_HOME - No user input is concatenated into file paths - realpath() used to canonicalise any configured paths - Unit test: paths with ../ are rejected

| US-19 | Security audit and static analysis pass | Priority: High | Points: 5 | Sprint: 5 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Codebase passes gcc -Wall -Wextra -Wshadow -Wformat-security - cppcheck or clang-tidy run with zero high-severity findings - No calls to gets, scanf("%s"), system(), or popen() - SECURITY.md documents threat model and mitigations

## EP-06 — Build, Test & Documentation

Makefile, unit tests (using C test harness), and developer documentation.

| US-20 | Makefile with install and clean targets | Priority: High | Points: 3 | Sprint: 1 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - make builds the binary - make install copies to PREFIX/bin - make clean removes all build artifacts - make test runs the test suite

| US-21 | Unit tests for parser and storage modules | Priority: High | Points: 8 | Sprint: 3 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - Date parser tests cover 10+ formats including edge cases - Storage tests cover CRUD and corruption recovery - Tests run without root and leave no side effects - CI-friendly: exits 0 on pass, non-zero on failure

| US-22 | Man page (ohbobi.1) | Priority: Low | Points: 3 | Sprint: 5 |
| --- | --- | --- | --- | --- |

Acceptance Criteria - man ohbobi renders correctly - All commands and flags documented - EXAMPLES section included

# 5. Sprint Schedule

Each sprint is assumed to be 2 weeks. The schedule below is calibrated for a team of 2–3 developers (typical for a course project team). Velocity estimate: ~25–30 points per sprint.

## Sprint 1

| Sprint Goal | Walking skeleton: CLI boots, dispatches commands, input sanitisation, Makefile |
| --- | --- |
| Stories | US-01 · US-02 · US-03 · US-04 · US-20 |

Total story points: 21

## Sprint 2

| Sprint Goal | Storage layer complete; single-day meal plan creation working end-to-end |
| --- | --- |
| Stories | US-05 · US-06 · US-07 · US-08 · US-17 · US-18 |

Total story points: 31

## Sprint 3

| Sprint Goal | Weekly plan mode, conflict handling, inline editor, unit tests, daily grid view |
| --- | --- |
| Stories | US-09 · US-10 · US-11 · US-12 · US-21 |

Total story points: 37

## Sprint 4

| Sprint Goal | Full grid viewer with weekly/monthly views, vim navigation, ANSI theme |
| --- | --- |
| Stories | US-13 · US-14 · US-15 · US-16 |

Total story points: 26

## Sprint 5

| Sprint Goal | Hardening, static analysis, man page, full regression test pass, release |
| --- | --- |
| Stories | US-19 · US-22 |

Total story points: 8

# 6. Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | Grid re-render completes in <50 ms on a 2015-era laptop |
| NFR-02 | Portability | Compiles and runs on Linux (glibc), macOS (libc), and WSL2 |
| NFR-03 | Standard | All C code is written to the C23 standard (ISO/IEC 9899:2024) |
| NFR-04 | Security | No user input is ever passed to a shell. No UB per UBSan at runtime. |
| NFR-05 | Accessibility | Respects NO_COLOR, TERM=dumb; all info available without colour |
| NFR-06 | Storage | Data file does not exceed 10 MB for 5 years of daily meal plans |
| NFR-07 | Correctness | Date parsing passes a property-based fuzz test of 10,000 random date strings |

# 7. Risk Register

| ID | Severity | Risk | Description | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | High | Terminal compatibility | Unicode box-drawing fails on Windows cmd.exe | Detect TERM; fall back to ASCII borders |
| R-02 | Medium | Date parsing complexity | Edge cases in locale-specific formats | Restrict to English formats; document scope clearly |
| R-03 | Medium | Binary file corruption | Power loss during write corrupts data | Atomic write (temp + rename) + CRC32 validation |
| R-04 | Low | Screen size detection | ioctl(TIOCGWINSZ) unavailable in some environments | Default to 80 cols if detection fails |
| R-05 | High | Buffer overflows | Course exercise may have less experienced devs | Mandatory code review; clang-tidy in CI |